## Q58 (hidden)
Status of Sewer Rehabilitation Projects in the Rock Creek Park
P6 Code | Project | Description | NEPA | Status | Design Start | Construction Start | Project Finish Date | Remark (COVID Impact)
A419 | Watts Branch Sewer Rehabilitation | This project is to design and construct sanitary sewer interceptors, trunk sewers and force mains identified as requiring upgrade by the major planning and condition assessment program underway for the sanitary sewer system. This project is needed to construct new and rehabilitate or replace aged infrastructure to restore integrity and reliability of DC Water's sanitary sewer system. |  | In Construction | 01-Jun-07 A | 29-Oct-08 A | 2021-03-31
A432 | Inflatable Dam Interim Upgrades | This project will assess the inflatable dams and make recommendations for replacement and/or interim improvements required. The dams in the system operate in conjunction with the Main and O Street Pumping Stations to manage combined sewer overflows within the system. Dams will be replaced with in-kind dams, which will include replacement of the rubber bladder, anchors, and mechanical components associated with the dam operation. Several inflatable dams need new air compressors and repairs to ancillary safety equipment, such as emergency telephones, ladders, and exhaust fans as part of this project. |  | In Design. Deferred as part of COVID spending limitation | 8-Aug-18 A | 2022-06-23 | 2024-06-22
A433 | A433 Spring Place Sewer Rehab | This project is to design and construct sanitary sewer interceptors, trunk sewers and force mains identified as requiring upgrade by the major planning and condition assessment program underway for the sanitary sewer system. This project is needed to construct new and rehabilitate or replace aged infrastructure to restore integrity and reliability of DC Water's sanitary sewer system. |  | In Design. Intermediate design in progress. Deferred as part of COVID spending limitation | 03-Feb-15 A | 2023-07-13 | 2025-07-12
BO12 | Spring Place Storm Manhole Rehab | This project provides design and construction services for stormwater sewer interceptors, trunk sewers and force mains that require upgrades. |  | In Design. Waiting to restart the project. Final design activity was deferred due to COVID spending limitation | 03-Feb-15 A | 2021-10-25 | 2023-04-22
DN26 | Heavy Cleaning of Oxon Run | The program will provide an ongoing effort to further inspect the Authority’s existing sewer system. |  | Inspections - Ongoing | N/A | 02-May-17 A | 2021-02-01
DN27 | Heavy Cleaning of PFM Siphons | The program will provide an ongoing effort to further inspect the Authority’s existing sewer system. |  | Not Started | N/A | 2021-10-01 | 2022-09-30
DN28 | Heavy Cleaning of B Street/New Jersey Ave | The program will provide an ongoing effort to further inspect the Authority’s existing sewer system. |  | Ongoing | N/A | 1-Jun-18 A | 2022-09-30
DN41 | Sewer IDIQ Inspection/Condition Assessment 1 | The program will provide an ongoing effort to further inspect the Authority’s existing sewer system. |  | Inspections - Ongoing | N/A | 1-Apr-19 A | 2027-11-19
DN42 | Sewer IDIQ Inspection/Condition Assessment 2 | The program will provide an ongoing effort to further inspect the Authority’s existing sewer system. |  | Inspections - Ongoing | N/A | 1-Apr-19 A | 2029-11-07
DR02 | Low Area Trunk Sewer - Rehabilitation | This project provides for the cleaning, assessing, design and rehabilitation of the 11,700 foot long Low Area Trunk Sewer after a collapse of a section of the sewer near the US Capitol Building. |  | Under Construction | 20-Jul-11 A | 2018-07-12 | 2021-01-31
FW01 | Piney Branch Sewershed Rehab, Phase 1 | This project will rehabilitate a portion of the Piney Branch Trunk Sewer. |  | In Design. Final design is submitted. All permits are obtained. Waiting for funds to start construction procurement. Deferred due to COVID spending limitation | 02-Sep-14 A | 2021-07-31 | 2024-07-28
G100 | Lining & Repair of Local Sewers | This project to rehabilitate and repair local sewers throughout the District is one aspect of the Service Life Improvement Plan outlined in the 2009 Sewer System Facilities Plan. |  | Construction Complete but Construction Management is still open | 01-Jun-11 A | 14-Jul-15 A | 2021-01-31
G101 | Rehab of Sewers in Georgetown | This project to rehabilitate and repair local sewers throughout the District is one aspect of the Service Life Improvement Plan outlined in the 2009 Sewer System Facilities Plan. |  | Construction complete but Legal Services activity is still open | 27-Sep-11 A | 16-Nov-16 A | 2021-01-31
G102 | Barry Rd. Sanitary Sewer | This project to rehabilitate and repair local sewers throughout the District is one aspect of the Service Life Improvement Plan outlined in the 2009 Sewer System Facilities Plan. |  | Construction Complete but Construction Management is still open | 31-Jan-13 A | 05-Dec-14 A | 2021-06-30
G204 | Rehab of Gates Structures 5A, 5B & 5C | This project includes rehabilitation of the sluice gates at Structures 5A, 5B, 5C, and the gate at the old Poplar Point Pumping Station. |  | In Planning | 2021-02-28 | 2022-08-14 | 2024-02-09
G501 | Creekbed Sewer Rehabilitation Glover Archbold Park | This project includes rehabilitation of approximately 20,400 linear feet of sanitary pipe, repair of 67 manholes, protection of 11 exposed pipes in stream crossings, and repair of 7 exposed manholes. | Yes | In Design. | 30-Jun-11 A | 2023-03-06 | 2028-09-08 | Design re-start in Sept 2022. NEPA document with NPS. Delayed due to COVID spending limitation
G502 | Creekbed Sewer Rehabilitation Soapstone Valley | This project includes rehabilitation of approximately 6,200 linear feet of sanitary pipe in the Soapstone Valley sewer system, repair of 29 manholes, asset protection of exposed assets, and rehabilitation of 2 MS4 outfalls. | Yes | In Design. | 30-Jun-11 A | 2021-06-01 | 2023-11-28
G503 | Creekbed Sewer Rehabilitation Foundry Branch | This project consists of multiple jobs to protect infrastructure in the vicinity of streams and creeks located throughout the District. The project intends to relocate and rehabilitate manholes and sewer pipes vulnerable to flooding or erosion and infrastructure exposed to or adjacent to surface waters. The project also includes the rehabilitation of outfalls and other tasks required to protect exposed sewers due to stream bank erosion. | Yes | In Design. | 30-Jun-11 A | 2023-03-06 | 2028-09-08 | Same as G501. There are plans to advertise the two as one Contract. NEPA document with NPS. Delayed due to COVID spending limitation
G504 | Creekbed Sewer Rehabilitation Klingle Valley | This project consists of multiple jobs to protect infrastructure in the vicinity of streams and creeks located throughout the District. The project intends to relocate and rehabilitate manholes and sewer pipes vulnerable to flooding or erosion and infrastructure exposed to or adjacent to surface waters. The project also includes the rehabilitation of outfalls and other tasks required to protect exposed sewers due to stream bank erosion. | Yes | Under Construction | 07-Jul-14 A | 01-Aug-16 A | 2021-07-31
G505 | Creekbed Sewer Rehabilitation Normanstone Park | This project consists of multiple jobs to protect infrastructure in the vicinity of streams and creeks located throughout the District. The project intends to relocate and rehabilitate manholes and sewer pipes vulnerable to flooding or erosion and infrastructure exposed to or adjacent to surface waters. The project also includes the rehabilitation of outfalls and other tasks required to protect exposed sewers due to stream bank erosion. | Yes | In Design. DDOT Point Repair Complete. | 07-Jul-14 A | 2023-01-31 | 2024-01-30
G506 | Creekbed Sewer Rehabilitation Shelia's Tributary (Broad Branch) | This project includes rehabilitation of 3,310 feet ranging from 8-inch to 15-inch diameter sewer pipe, stream improvements, and protection and repair of 6 exposed sewer crossings along 30th Street, Newlands Park, and Sheila's Tributary. | Yes | In Planning. | 2027-03-03 | 2029-02-27 | 1930-08-28 | Project deferred due to budget limitation
G603 | Sanitary Sewer Rehab and Repair Phase 4 | This project rehabilitates sanitary sewers located under buildings citywide. Other activities included in this project are cleaning, pre- and post-CCTV, sealing joints and repair of offset pipe. |  | Design complete. Deferred due to COVID spending limitations | 01-Jul-14 A | 2024-03-28 | 2025-09-23
G703 | Comb Sewer Rehab and Repair Phase 4 | High Priority rehabilitation projects that needed to be undertaken to fix structural defects and restore structural integrity of the sewer system. Other activities included in this project are cleaning, pre and post CCTV, sealing joints and repair of offset pipe. |  | Design complete. Deferred due to COVID spending limitations | 02-Jul-14 A | 2024-03-28 | 2025-09-23
G712 | Spring Place Combined Sewer Rehab | High Priority rehabilitation projects that needed to be undertaken to fix structural defects and restore structural integrity of the sewer system. Other activities included in this project are cleaning, pre and post CCTV, sealing joints and repair of offset pipe. |  | In Design. Deferred due to COVID spending limitation | 03-Feb-15 A | 2023-07-13 | 2025-07-12
GA01 | Small Local Sewer Rehab 4 | This project to rehabilitate and repair local sewers throughout the District is one aspect of the Service Life Improvement Plan outlined in the 2009 Sewer System Facilities Plan. |  | Construction Complete but Construction Management is still open | 03-Apr-14 A | 03-Apr-15 A | 2021-01-31
GH01 | Large Sewer Rehab 3 | This project to rehabilitate and repair local sewers throughout the District is one aspect of the Service Life Improvement Plan outlined in the 2009 Sewer System Facilities Plan. |  | In Design. Deferred due to COVID spending limitation | 16-Jan-14 A | 2023-05-06 | 2025-10-31
GY03 | Storm Sewer Rehab and Repair Phase 4 | This multi-job project rehabilitates storm sewers located throughout the District. Multiple jobs provide the annualized program to rehabilitate the storm sewer inventory which exhibits deteriorated conditions and is located under buildings. |  | Design complete. Deferred due to COVID spending limitations | 02-Jul-14 A | 2024-03-28 | 2025-09-23
H600 | FY2018 - DSS Sanitary Sewer Projects | This project is for the annual program of planned projects by the Department of Sewer Services for the rehabilitation and improvement of the sanitary sewer |  | Ongoing | N/A | 26-Sep-18 A | 2021-05-03
HN01 | FY2019 - DSS Sanitary Sewer Projects | This project is for the annual program of planned projects by the Department of Sewer Services for the rehabilitation and improvement of the sanitary sewer |  | Ongoing | N/A | 19-May-19 A | 2021-12-31
HT07 | Rehabilitation of Anacostia Force Main | This job was initially set up to provide funding for the design and construction of a diversion structure along the Anacostia Force Main (AFM) as a result of the South Capitol Bridge construction project. Due to schedule and budget constraints, the design of the diversion structure was cancelled and the budget was used to fund the geotechnical monitoring of the AFM during the bridge construction. |  | In Planning | 1-Apr-19 A | N/A | 2022-05-30
IF02 | Sanitary Sewer Rehab and Repair Phase 6 | This multi-job project to rehabilitate combined sewers in various locations throughout the District is one aspect of the Service Life Improvement Plan outlined in the Sewer System Facilities Plan. Multiple jobs provide the annualized program to rehabilitate the large sewer inventory which exhibit deteriorated conditions. |  | In Design. Pre-final phase. Permitting and contract procurement can proceed when funds becomes available. Work will be executed as under IH02. Deferred due to COVID spending limitation | 20-Aug-14 A
IH02 | Comb Sewer Rehab and Repair Phase 7 | This multi-job project to rehabilitate combined sewers in various locations throughout the District is one aspect of the Service Life Improvement Plan outlined in the Sewer System Facilities Plan. Multiple jobs provide the annualized program to rehabilitate the large sewer inventory which exhibit deteriorated conditions. |  | In Design. Pre-final phase. Permitting and contract procurement can proceed when funds becomes available. Deferred due to COVID spending limitation | 29-Oct-14 A | 2024-03-29 | 2026-09-24
IK01 | Potomac Force Main Assessment | Condition assessment of the Potomac Force Main to determine rehabilitation needs. |  | Inspection | N/A | 2021-01-01 | 2022-01-02
IL01 | Creekbed Sewer Rehabilitation Pinehurst Branch (West) | This project consists of rehabilitation of about 5,700 linear feet of pipe, manhole rehabilitation, and stream stabilization at 3 crossings to protect sewer assets | Yes | In Design. | 22-Jul-14 A | 2023-07-05 | 2024-06-12 | Projects would be done in collaboration with DOEE. Contact DOEE for status update
IL02 | Creekbed Sewer Rehabilitation Dumbarton Oaks | Project evaluates sewer assets in Dumbarton Oaks Park and includes the possible rehabilitation of 3,800 linear feet of sewer along a stream that runs from Whitehaven Street, NW to Rock Creek. | Yes | In Planning. | 2022-06-30 | 2026-08-28 | 2028-02-26 | Deferred due to COVID spending limitation
IL04 | Creekbed Sewer Rehabilitation Fort Stanton Park Irving & Suitland Parkway | This project consists of multiple jobs to protect infrastructure in the vicinity of streams and creeks located throughout the District. The project intends to relocate and rehabilitate manholes and sewer pipes vulnerable to flooding or erosion and infrastructure exposed to or adjacent to surface waters. The project also includes the rehabilitation of outfalls and other tasks required to protect exposed sewers due to stream bank erosion. |  | In Design. Pipe rehab & asset protection contracted through MOU with DOEE; Waiting for design from DOEE | 21-Aug-17 A | 2021-01-30 | 2023-01-26
IL05 | Creekbed Sewer Rehabilitation Rock Creek Sherrill Drive & Beach Drive | This project involves the inspection, assessment, and design of rehabilitation and asset protection of existing and exposed pipe within the creek to address the structural and operational defects and design stream restoration, if deemed necessary, to prevent further erosion. This project includes the examination of possible rehabilitation and/or replacement of about 1,318 linear feet of sewer, ranging from 12 to 18 inches diameter, and 7 manholes | Yes | In Planning. | 2023-10-01 | 2026-03-02 | 2027-08-31 | Deferred due to COVID spending limitation
IL06 | Creekbed Sewer Rehabilitation Fenwick Branch E Beach Dr & Red Bud Lane | This project includes rehabilitation of about 8,325 linear feet of pipe, manhole rehabilitation, stream stabilization, and rehabilitation of 3 MS4 outfalls | Yes | In Design. | 22-Jul-14 A | 2023-12-03 | 2026-12-03 | NEPA and CFR complete. Final design to re-start July 2021. Deferred due to COVID spending limitation
IL10 | Creekbed Sewer Rehabilitation Rock Creek Oregon Avenue | This project consists of multiple jobs to protect infrastructure in the vicinity of streams and creeks located throughout the District. The project intends to relocate and rehabilitate manholes and sewer pipes vulnerable to flooding or erosion and infrastructure exposed to or adjacent to surface waters. The project also includes the rehabilitation of outfalls and other tasks required to protect exposed sewers due to stream bank erosion and abandonment of Pinehurst sewers | No | Under Construction. | 03-Dec-15 A | 30-Sep-16 A | 2022-08-02 | Pipes for abandonment are in design phase. To be executed along with IL01
IL11 | Creekbed Sewer Rehabilitation Spring Valley | This project consists of multiple jobs to protect infrastructure in the vicinity of streams and creeks located throughout the District. The project intends to relocate and rehabilitate manholes and sewer pipes vulnerable to flooding or erosion and infrastructure exposed to or adjacent to surface waters. The project also includes the rehabilitation of outfalls and other tasks required to protect exposed sewers due to stream bank erosion. |  | Under Construction | 20-Nov-14 A | 11-Mar-17 A | 2021-10-31
IN02 | Rehab of Upper East Side Interceptor Phase 1 | The scope includes rehabilitation of portions of the Upper East Side Interceptor and adjacent small sewers |  | In Planning | 2022-02-12 | 2026-04-08 | 2027-09-30
J001 | B Street/New Jersey Ave. Trunk Sewer Rehab and Cleaning Phase 1 | This project involves a condition assessment, design, and repair of the B Street / New Jersey Avenue trunk sewer. |  | Under Construction | 02-Oct-16 A | 21-May-18 A | 2021-06-30
J306 | National Arboretum Sewer Rehab (Eastside Interceptor) | This project is for the assessment, design and construction of sanitary sewer interceptors, trunk sewers and force mains that require upgrade. |  | Construction complete but DSDC Archaeological services activity is still active | 28-Jan-10 A | 15-Jul-16 A | 2021-03-30
J307 | National Arboretum Sewer Rehab Construction Contract 2 | This project is for the assessment, design and construction of sanitary sewer interceptors, trunk sewers and force mains that require upgrade. |  | In Design | 01-Jun-20 A | 2021-02-02 | 2021-07-31
JH01 | FY2020 - DSS Storm Sewer Projects | This project is for the annual program of planned projects by the Department of Sewer Services for the rehabilitation and improvement of the stormwater sewer system. This project is needed to replace aged infrastructure to restore integrity and reliability of the stormwater sewer system. |  | Ongoing | N/A | 20-Nov-19 A | 2022-07-30
JI00 | FY2020 - DSS Sanitary Sewer Projects | This project is for the annual program of planned projects by the Department of Sewer Services for the rehabilitation and improvement of the sanitary sewer |  | Ongoing | N/A | 24-Sep-19 A | 2022-05-03
JX01 | Sanitary Sewer Rehabilitation 10 | This project to rehabilitate and repair local sewers throughout the District is one aspect of the Service Life Improvement Plan outlined in the 2009 Sewer System Facilities Plan. |  | In Design. Deferred due to COVID spending limitation | 26-Sep-17 A | 2023-03-03 | 2025-06-19
LN00 | FY2021 - DSS Sanitary Sewer Projects | This project is for the annual program of planned projects by the Department of Sewer Services for the rehabilitation and improvement of the sanitary sewer |  | Not Started | N/A | 2021-02-01 | 2021-10-01
LO00 | FY2021 - DSS Storm Sewer Projects | This project is for the annual program of planned projects by the Department of Sewer Services for the rehabilitation and improvement of the stormwater sewer system. This project is needed to replace aged infrastructure to restore integrity and reliability of the stormwater sewer system. |  | Ongoing | N/A | 01-Dec-20 A | 2022-08-26
LZ01 | Annual Inspection and Cleaning & Corrosion Mitigation | Inspection and cleaning of the Potomac Interceptor. |  | In Planning | N/A | 19-Jun-15 A | 2023-11-25
LZ02 | PI Access Road | Rehabilitate access roads along the PI previously identified. The plan is to reactivate the old project originally designed by CCJM by verifying what was accomplished, permitting wetlands disturbance through MD and VA, and sediment control measures through local counties. |  | In Planning | 2022-01-21 | 2023-06-30 | 2024-06-24
LZ03 | PI Phase 1 Pipe Rehab at Clara Barton Pkwy | This project will rehabilitate segments of the Potomac Interceptor (PI) Sewer. The project will include engineering services for the design, permitting, bid, and construction phases and funding for capital construction, construction management, and site access planning. |  | In Design | 2-Feb-18 A | 2025-01-15 | 2027-01-14
LZ04 | PI Phase 2 Pipe Rehab at Potomac Crossing | This project will rehabilitate segments of the Potomac Interceptor (PI) Sewer. The project will include engineering services for the design, permitting, bid, and construction phases and funding for capital construction, construction management, and site access planning. |  | In Design | 25-Feb-20 A | 2025-04-09 | 2029-04-14
LZ06 | PI Phase 4 Pipe Rehab at Fairfax and Loudon Co. | This project rehabilitates the portion of the Potomac Interceptor between M-44 and M-43, located in Fairfax and Loudon County. |  | In Design | 20-Dec-19 A | 2021-10-04 | 2023-04-07
LZ07 | PI Phase 5 Pipe Rehab at Fairfax PI Tunnel | This project will rehabilitate segments of the Potomac Interceptor (PI) Sewer. The project will include engineering services for the design, permitting, bid, and construction phases and funding for capital construction, construction management, and site access planning. |  | In Design | 09-Jan-20 A | 2021-05-13 | 2022-08-04
LZ08 | PI Phase Pre-Design Planning | This project provides funding for various studies and other support that aids in the development of CIP projects for the Potomac Interceptor. These tasks include, but is not limited to, NEPA support, ROE and easement studies, and Potomac Interceptor Renewal Report. |  | In Planning | 01-May-16 A | N/A | N/A
LZ09 | PI Phase 6 Pipe Rehab | This project rehabilitates the portion of the Potomac Interceptor. Location to be determined |  | In Design | 25-Aug-20 A | 2022-12-01 | 2024-11-28
LZ12 | PI Corrosion Prevention | his job employs corrosion prevention measures to various assets along the Potomac Interceptor. |  | In Planning | 2021-09-28 | 2022-07-27 | 2023-07-27
LZ13 | PI Manhole Rehabilitation | This job rehabilitates manholes that are not part of any pipe rehabilitation project for the Potomac Interceptor. |  | In Planning | 2021-01-01 | 2022-06-17 | 2023-07-17
LZ14 | PI Cabin John Culvert Headwall and Embankment Repair | This project includes installation of concrete blocks or equivalent on either side of the Cabin John culvert located just downstream of PI MH 11. This culvert has been subject to flooding mainly due to huge driftwood trunks flooded at the upstream side of the culvert during heavy storm. Due to the flood, the upstream side of the culvert headwall was subject to erosion which exposes the Potomac Interceptor. |  | In Design | 2021-03-01 | 2024-04-26 | 2025-10-22
LZ15 | PI Manhole Rehabilitation | This job rehabilitates manholes that are not part of any pipe rehabilitation project for the Potomac Interceptor. |  | In Planning | 2022-10-24 | 2024-01-03 | 2024-12-28
LZ16 | Potomac Interceptor Route 7 Crossing | This job rehabilitates the portion of the Potomac Interceptor which crosses Route 7 as part of VDOT project |  | In Design |  | 2021-01-01 | 2022-12-31
PJ01 | Re-Activation of Old Anacostia Force Main (AFM) Gravity Main | This project is to rehabilitate the old Anacostia Force Main (AFM) so that it can behave as a relief sewer for the 108-inch diameter AFM. The AFM extends 32,700 linear feet from the Maryland / District border to its terminus near South Capital Street and Firth Sterling Ave, SE and is within National Park Service property (NPS). The AFM carries approximately 244 MGD (1/3 of WSSC’s wastewater flow) to Blue Plains. This critical sewer consists largely of pre-stressed concrete cylinder pipe (PCCP) which has a history of failures throughout the industry. |  | In Planning | N/A | 1-Jun-18 A | 2022-01-02
QS02 | Local Sewer Rehab 5-2 | This project rehabilitates sewers in various locations within the District in association with the Sewer Rehabilitation Program identified in the Sewer System Facility Plan (SSFP). Project activities include pre-cleaning and closed-circuit television (CCTV) inspection to verify the proposed rehabilitation method, pipeline rehabilitation using trenchless technologies or excavated point repairs as necessary, lateral connection repairs, and manhole rehabilitation. |  | In Planning | 2021-07-16 | 2022-12-16 | 2024-06-15
QS05 | Permit Services for Georgetown, Atlas District, Columbia Heights, Manor Park, and Bloomingdale | Provides permit services funding for local sewer rehab projects (GH01, IH02/IF02, G703/G603/GY03) |  | In Design. Waiting for the local sewer rehab projects to restart. Deferred due to COVID spending limitation | 2021-12-01 |  | 2024-09-28
QX01 | Local Sewer Assessment 1-1 | This project(s) addresses the need to fund future Local Sewer Inspection Program (LSIP) once DETS approval is obtained and mileage goals are set. This program involves the inspection of gravity sewers less than 60-inch; inspection involves mainly CCTV, sonar, as well as light & heavy cleaning (if desired and as needed). |  | Not Started | N/A | 31-Mar-20 A | 2023-09-29
RA01 | Major Sewer Assessment & Heavy Cleaning 1-1 | This project(s) addresses the need to fund future Heavy Cleaning contracts and/or supplement or wholly fund the heavy cleaning of selected major sewers, as needed. It will also be utilized to supplement the DN41 and DN42 projects and fund the Sewer component of the Pipe Condition Assessment (PCA) program. Such sewers may include the Anacostia Siphons, the Potomac Force Main Siphons the East Side Interceptor and NE Boundary Sewer cleaning. |  | Not Started | N/A | 2021-01-01 | 2025-10-15
RA02 | Major Sewer Assessment & Heavy Cleaning 1-2 | This project(s) addresses the need to fund future Heavy Cleaning contracts and/or supplement or wholly fund the heavy cleaning of selected major sewers, as needed. |  | Not Started | N/A | 2021-09-30 | 2022-09-29
RC01 | Rehabilitation of Rock Creek Main Interceptor and Beach Drive Sewers | This project will rehabilitate the Rock Creek Main Interceptor (RCMI) and RCMI Relief Sewer (RCMIRS). |  | In Planning | 2021-09-29 | 2026-06-02 | 2027-12-01
RC04 | Major Sewer Rehab 1-2 | Establishes a program for rehabilitation of major sewers as the need is identified from inspections and condition assessments. |  | In Planning | 2022-02-04 | 2023-07-14 | 2025-01-04
RC07 | Major Sewer Rehab 1-5 Northeast Boundary Sewer | Establishes a program for rehabilitation of major sewers as the need is identified from inspections and condition assessments. This job was assigned to rehabilitate portions of the Northeast Boundary Trunk Sewer |  | In Design | 2021-01-01 | 2023-02-20 | 2025-02-20
RD03 | Oxon Run Sewer Rehabilitation | The scope of this project includes design for the relocation of the Valley Terrace connection to Upper Oxon Run; abandonment of pipes; encasement repair; and rehabilitation of Lower Oxon Run Interceptor, Lower Oxon Run Interceptor Relief, Oxon Run Interceptor, and Upper Oxon Run Interceptor |  | In Design. Design and construction will be part of DOEE Oxon Run stream restoration project | 2021-04-01 | 2025-05-27 | 2026-11-18
IM05 | Creekbed Sewer Rehabilitation Oregon Ave at St. Johns | Rehabilitation of an existing gravity-flow sanitary sewer, 1,800 feet long, 15" vitrified clay pipe, with eight brick manholes, all built in 1927. The sewer serves about 35 single-family homes and St. John's College HS, and is located in NW Washington between Oregon Avenue and Beach Drive, inside NPS Rock Creek Park. | Yes | In Planning. | 2022-01-19 | 2026-03-16 | 2027-09-06 | Deferred due to COVID spending limitation
IM09 | Joyce Road/Morrow Drive Sewer Rehabilitation | This project involves inspection, assessment, and design of rehabilitation and asset protection of existing and exposed pipe within the creek to address the structural and operational defects and design stream restoration to prevent further erosion. The project includes sewers near creek crossings located along Joyce Road NW stretching from 16th Street NW to Military Road NW in the Brightwood neighborhood, sewers located in between Galloway Street NE and Gallatin Street NE, in the Michigan Park neighborhood, and sewers located in between Morrow Drive NW and Beach Drive NW near the NPS Park Police's 3rd District headquarters. This project involves a total of approximately 3,220 linear feet of sewers, ranging from 8-inch diameter to 24-inch diameter. Pipe materials include vitrified clay pipe, reinforced concrete pipe, and PVC. of approximately 3,220 linear feet of sewers, ranging from 8-inch diameter to 24-inch diameter. Pipe materials include vitrified clay pipe, reinforced concrete pipe, and PVC. | Yes | In Planning. | 2026-01-01 | 1930-03-01 | 1931-03-04 | Deferred due to COVID spending limitation

## Rock Creek
Status of Sewer Rehabilitation Projects in the Rock Creek Park
P6 Code | Project | Description | NEPA | Status | Design Start | Construction Start | Project Finish Date | Remark (COVID Impact)
G501 | Creekbed Sewer Rehabilitation Glover Archbold Park | This project includes rehabilitation of approximately 20,400 linear feet of sanitary pipe, repair of 67 manholes, protection of 11 exposed pipes in stream crossings, and repair of 7 exposed manholes. | Yes | In Design. | 30-Jun-11 A | 2023-03-06 | 2028-09-08 | Design re-start in Sept 2022. NEPA document with NPS. Delayed due to COVID spending limitation
G502 | Creekbed Sewer Rehabilitation Soapstone Valley | This project includes rehabilitation of approximately 6,200 linear feet of sanitary pipe in the Soapstone Valley sewer system, repair of 29 manholes, asset protection of exposed assets, and rehabilitation of 2 MS4 outfalls. | Yes | In Design. | 30-Jun-11 A | 2021-06-01 | 2023-11-28
G503 | Creekbed Sewer Rehabilitation Foundry Branch | This project consists of multiple jobs to protect infrastructure in the vicinity of streams and creeks located throughout the District. The project intends to relocate and rehabilitate manholes and sewer pipes vulnerable to flooding or erosion and infrastructure exposed to or adjacent to surface waters. The project also includes the rehabilitation of outfalls and other tasks required to protect exposed sewers due to stream bank erosion. | Yes | In Design. | 30-Jun-11 A | 2023-03-06 | 2028-09-08 | Same as G501. There are plans to advertise the two as one Contract. NEPA document with NPS. Delayed due to COVID spending limitation
G504 | Creekbed Sewer Rehabilitation Klingle Valley | This project consists of multiple jobs to protect infrastructure in the vicinity of streams and creeks located throughout the District. The project intends to relocate and rehabilitate manholes and sewer pipes vulnerable to flooding or erosion and infrastructure exposed to or adjacent to surface waters. The project also includes the rehabilitation of outfalls and other tasks required to protect exposed sewers due to stream bank erosion. | Yes | Construction of sewer along stream is complete. | 07-Jul-14 A | 01-Aug-16 A | 2021-07-31
G505 | Creekbed Sewer Rehabilitation Normanstone Park | This project consists of multiple jobs to protect infrastructure in the vicinity of streams and creeks located throughout the District. The project intends to relocate and rehabilitate manholes and sewer pipes vulnerable to flooding or erosion and infrastructure exposed to or adjacent to surface waters. The project also includes the rehabilitation of outfalls and other tasks required to protect exposed sewers due to stream bank erosion. | Yes | Trenchless components in Design. Excavated components were completed within DDOT project. | 07-Jul-14 A | 2023-01-31 | 2024-01-30
G506 | Creekbed Sewer Rehabilitation Shelia's Tributary (Broad Branch) | This project includes rehabilitation of 3,310 feet ranging from 8-inch to 15-inch diameter sewer pipe, stream improvements, and protection and repair of 6 exposed sewer crossings along 30th Street, Newlands Park, and Sheila's Tributary. | Yes | In Planning. | 2027-03-03 | 2029-02-27 | 1930-08-28 | Project deferred due to budget limitation. Applying for BRIC grant.
IL01 | Creekbed Sewer Rehabilitation Pinehurst Branch (West) | This project consists of rehabilitation of about 5,700 linear feet of pipe, manhole rehabilitation, and stream stabilization at 3 crossings to protect sewer assets | Yes | In Design. | 22-Jul-14 A | 2023-07-05 | 2024-06-12 | Projects would be done in collaboration with DOEE. Contact DOEE for status update
IL02 | Creekbed Sewer Rehabilitation Dumbarton Oaks | Project evaluates sewer assets in Dumbarton Oaks Park and includes the possible rehabilitation of 3,800 linear feet of sewer along a stream that runs from Whitehaven Street, NW to Rock Creek. | Yes | In Planning. | 2022-06-30 | 2026-08-28 | 2028-02-26 | Deferred due to COVID spending limitation
IL05 | Creekbed Sewer Rehabilitation Rock Creek Sherrill Drive & Beach Drive | This project involves the inspection, assessment, and design of rehabilitation and asset protection of existing and exposed pipe within the creek to address the structural and operational defects and design stream restoration, if deemed necessary, to prevent further erosion. This project includes the examination of possible rehabilitation and/or replacement of about 1,318 linear feet of sewer, ranging from 12 to 18 inches diameter, and 7 manholes | Yes | In Planning. | 2023-10-01 | 2026-03-02 | 2027-08-31 | Deferred due to COVID spending limitation. Applying for BRIC grant.
IL06 | Creekbed Sewer Rehabilitation Fenwick Branch E Beach Dr & Red Bud Lane | This project includes rehabilitation of about 8,325 linear feet of pipe, manhole rehabilitation, stream stabilization, and rehabilitation of 3 MS4 outfalls | Yes | In Design. | 22-Jul-14 A | 2023-12-03 | 2026-12-03 | NEPA and CFR complete. Final design to re-start July 2021. Deferred due to COVID spending limitation
IL10 | Creekbed Sewer Rehabilitation Rock Creek Oregon Avenue | This project consists of multiple jobs to protect infrastructure in the vicinity of streams and creeks located throughout the District. The project intends to relocate and rehabilitate manholes and sewer pipes vulnerable to flooding or erosion and infrastructure exposed to or adjacent to surface waters. The project also includes the rehabilitation of outfalls and other tasks required to protect exposed sewers due to stream bank erosion and abandonment of Pinehurst sewers | No | Construction physically complete, nearing closeout | 03-Dec-15 A | 30-Sep-16 A | 2022-08-02 | Pipes for abandonment are in design phase and will be done in partnership with DOEE. To be executed along with IL01
IM05 | Creekbed Sewer Rehabilitation Oregon Ave at St. Johns | Rehabilitation of an existing gravity-flow sanitary sewer, 1,800 feet long, 15" vitrified clay pipe, with eight brick manholes, all built in 1927. The sewer serves about 35 single-family homes and St. John's College HS, and is located in NW Washington between Oregon Avenue and Beach Drive, inside NPS Rock Creek Park. | Yes | In Planning. | 2022-01-19 | 2026-03-16 | 2027-09-06 | Deferred due to COVID spending limitation. Applying for BRIC grant.
IM09 | Joyce Road/Morrow Drive Sewer Rehabilitation | This project involves inspection, assessment, and design of rehabilitation and asset protection of existing and exposed pipe within the creek to address the structural and operational defects and design stream restoration to prevent further erosion. The project includes sewers near creek crossings located along Joyce Road NW stretching from 16th Street NW to Military Road NW in the Brightwood neighborhood, sewers located in between Galloway Street NE and Gallatin Street NE, in the Michigan Park neighborhood, and sewers located in between Morrow Drive NW and Beach Drive NW near the NPS Park Police's 3rd District headquarters. This project involves a total of approximately 3,220 linear feet of sewers, ranging from 8-inch diameter to 24-inch diameter. Pipe materials include vitrified clay pipe, reinforced concrete pipe, and PVC. of approximately 3,220 linear feet of sewers, ranging from 8-inch diameter to 24-inch diameter. Pipe materials include vitrified clay pipe, reinforced concrete pipe, and PVC. | Yes | In Planning. | 2026-01-01 | 1930-03-01 | 1931-03-04 | Deferred due to COVID spending limitation
RC01 | Rehab of Rock Creek Main Interceptor and Beach Drive Sewers | This project will rehabilitate the Rock Creek Main Interceptor (RCMI) and RCMI Relief Sewer (RCMIRS). The project also includes inspection of the RCMIRS. | Yes | In Planning. | 2021-09-29 | 2026-06-02 | 2027-12-01 | Deferred due to COVID spending limitation